# October close status notes

Fictional training material — all names and figures are invented.

As of 3 November 2026.

Alex: Bank reconciliation is in progress; one statement is missing. I expect to finish on 5 November.

Sam: Accrual review has not started; waiting for cost-centre estimates.

Priya: Intercompany balances need review. I understood Alex was the owner; the checklist has no owner.

Reporting cannot start until accruals and intercompany balances are reviewed.